## Rollout Scorecard
Rollout Gate-Criteria Scorecard — expand only when the gate is met
Audit-first, staged rollout. Do NOT advance to the next phase until every gate in the current phase is GREEN. Fill Measured value + Status; the gate is the rule.
Phase | Metric | Gate to advance | Measured value | Status | Notes
A — Build | Compile pipeline | scripts/compile.sh --check passes in CI
A — Build | Asset coverage | All 7 primitives have an owner + a committed source file
A — Build | Pilot context load | Pilot repo loads CLAUDE.md + copilot-instructions correctly
B — Pilot | Adoption | ≥ 80% of pilot team using the harness weekly
B — Pilot | Blocked-session rate | < 5% of sessions blocked by policy (false positives low)
B — Pilot | Review SLA | Median PR review time holds (no regression vs baseline)
B — Pilot | Self-reported value | > 25% self-reported productivity gain (survey)
B — Pilot | Security | 0 secrets merged; security-guard catching planted test issues
C — Department | Reliability / uptime | Harness services uptime ≥ 99.5% over the phase
C — Department | Blocked-session rate | < 3% blocked (tightened denies, still low friction)
C — Department | Audit completeness | 100% of agent actions traceable to an identity in SIEM
C — Department | Drift | 0 repos with config drifted from template (compile-check green)
C — Department | Feedback loop | Bad-block reports triaged within 1 week, < 10 open
D — Org-wide | Coverage | ≥ 90% of active repos onboarded (template or bootstrap)
D — Org-wide | Policy enforcement | managed-settings deployed to 100% of endpoints via MDM
D — Org-wide | Compliance evidence | Crosswalk complete; sample audit pull reproducible end-to-end
D — Org-wide | Sustained value | Productivity gain sustained; no rise in incident/escape rate
D — Org-wide | Ownership | Named owner + quarterly review cadence in place

## How to use
Rollout Gate-Criteria Scorecard — how to use
1. Work the phases in order: A Build → B Pilot → C Department → D Org-wide.
2. Each row is a gate. Fill 'Measured value' from your telemetry/surveys.
3. Set Status (Not measured / Red / Amber / Green) from the dropdown.
4. Advance to the next phase ONLY when every gate in the current phase is Green.
5. Keep a rollback path for each control — if a gate goes Red after advancing,
loosen the relevant deny/hook and drop back a phase.
The gates are deliberately measurable (a percentage, an uptime, a count) so the
decision to expand is driven by data, not vibes. Targets are starting points —
tune them to your org's risk appetite, but keep them concrete.
Mid-2026 snapshot. Treat the harness as a living product.